## Sheet1
Requirement ID | Requirement Type | Requirement Description | Test Case ID | Test Type | Test File / Path | Status | Last Updated | Evidence / Notes
FR-1 | Functional | Upload CSV files and accept JSON payloads for ingestion. | TC-FR-1-API-UPLOAD | System / API | tests/ingestion_upload/test_upload.py::test_upload_csv_success | Pass | 2025-12-04 | Covered by backend pytest run (84% overall coverage); validates successful CSV upload pathway and response envelope.
FR-2 | Functional | Ingest raw CSV/JSON into clean_events with schema validation and idempotency. | TC-FR-2-INGEST-JSON | System / API | tests/ingestion_upload/test_ingest_raw_json.py::test_ingest_json_valid_rows | Pass | 2025-12-04 | Confirms valid JSON rows are accepted, normalized, and counted correctly.
FR-3 | Functional | Compute daily KPIs and persist to metric_daily. | TC-FR-3-KPI-SERVICE | Unit + System | tests/kpi_metrics_engine/test_kpi_service_smoke.py::test_kpi_aggregation_smoke | Pass | 2025-12-04 | Verifies KPI aggregation logic and DB writes for metric_daily.
FR-4 | Functional | Provide rolling-window anomaly detection over daily metrics. | TC-FR-4-ANOMALY-API | System / API | tests/test_anomaly_api.py::test_anomaly_window_default | Pass | 2025-12-04 | Ensures rolling anomaly route returns expected structure and honors default window.
FR-4 | Functional | Provide rolling-window anomaly detection over daily metrics. | TC-FR-4-ANOMALY-UAT | UAT | tests/uat/test_anomaly_overlay_ua.py::test_anomaly_overlay_contract | Pass | 2025-12-04 | UAT contract for anomaly overlay used by dashboard.
FR-5 | Functional | Generate short-horizon forecasts with SARIMAX-backed engine. | TC-FR-5-FORECAST-CONTRACT | UAT | tests/uat/test_forecast_daily_contract_ua.py::test_forecast_daily_contract_schema | Pass | 2025-12-04 | Validates forecast daily contract (fields, ordering, horizon) for dashboard overlay.
FR-5 | Functional | Generate short-horizon forecasts with SARIMAX-backed engine. | TC-FR-5-FORECAST-E2E | System / API | tests/test_forecast_end_to_end_target_date.py::test_forecast_target_dates_align | Pass | 2025-12-04 | End-to-end test confirming forecast horizon aligns with last metric date.
FR-13 | Functional | Diagnose and safely fall back to naive constant forecast when SARIMAX cannot be used. | TC-FR-13-SARIMAX-FALLBACK | Unit | tests/unit/test_forecast_sarimax_fallback.py::test_sarimax_falls_back_when_insufficient_points | Pass | 2025-12-04 | Evidence that SARIMAX is bypassed and naive model is used when data is insufficient or model fails.
FR-6 | Functional | Expose daily metrics via API for dashboard charts and exports. | TC-FR-6-METRICS-API | System / API | tests/kpi_metrics_engine/test_metrics_api.py::test_metrics_api_basic | Pass | 2025-12-04 | Confirms metrics API returns expected schema and filters.
FR-8 | Functional | Export daily metrics as CSV for external analysis. | TC-FR-8-EXPORT-CSV | System / API | tests/ingestion_upload/test_export_csv_api.py::test_metrics_export_csv_contract | Pass | 2025-12-04 | Ensures CSV export endpoint schema and header layout match contract.
FR-9 | Functional | Schedule recurring jobs for KPI, forecast, and housekeeping tasks. | TC-FR-9-SCHEDULER-REGISTRATION | Unit / Integration | tests/scheduler/test_scheduler_registration.py::test_jobs_registered | Pass | 2025-12-04 | Verifies APScheduler jobs are registered and named correctly at startup.
FR-10 | Functional | Provide authentication with signup/login and token refresh for dashboard users. | TC-FR-10-AUTH-API | System / API | tests/test_auth_api.py::test_signup_and_login_flow | Pass | 2025-12-04 | Confirms signup, login, and token issuance flow works end-to-end.
FR-11 | Functional | Log structured request/response metadata for observability and diagnostics. | TC-FR-11-OBS-MW | Unit | tests/unit/test_observability_middleware.py::test_request_logging_envelope | Pass | 2025-12-04 | Validates observability middleware envelopes request metadata and emits structured logs.
FR-12 | Functional | Provide consistent error envelopes for API failures. | TC-FR-12-ERROR-ENVELOPES | System / API | tests/test_envelopes_and_errors.py::test_error_envelope_shapes | Pass | 2025-12-04 | Checks that errors follow the standardized envelope used by the frontend.
QR-1 | Quality | Maintain acceptable performance for ingestion and metrics queries under expected load. | TC-QR-1-COV-BUMP-FORECAST | Unit / Perf-adjacent | tests/unit/test_cov_bump_forecast.py::test_forecast_path_cov_bump | Pass | 2025-12-04 | Exercises forecast hot path and ensures code remains covered and efficient; additional perf tests tracked separately.
QR-4 | Quality | Enforce security headers, TLS, and basic hardening on all HTTP responses. | TC-QR-4-SEC-HEADERS | System / API | tests/test_security_headers.py::test_security_headers_present | Pass | 2025-12-04 | Confirms security headers (CSP, HSTS, frame options) are applied consistently.
QR-4 | Quality | Protect secrets and cryptographic operations for encrypted payload fields. | TC-QR-4-CRYPTO | Unit | tests/unit/test_crypto.py::test_round_trip_encrypt_decrypt | Pass | 2025-12-04 | Verifies Fernet-based encryption/decryption used for raw event payloads.
QR-5 | Quality | Maintain modular, testable code structure with high coverage for core services. | TC-QR-5-SERVICE-COVERAGE | Meta / Coverage | pytest --cov=app --cov-report=term-missing | Pass (84.14% overall) | 2025-12-04 | Evidence from coverage-report.txt demonstrating ≥80% coverage and good distribution across modules.
QR-6 | Quality | Provide a portable demo package using SQLite and setup scripts. | TC-QR-6-PORTABLE-README | Documentation / UAT | docs/README_PORTABLE.md (manual UAT) | Pass | 2025-12-04 | Manual walkthrough using start_all.sh / start_all.ps1 validated that a fresh user can run the demo end-to-end.
AR-4 | Architectural | Maintain up-to-date architecture and testing documentation under docs/. | TC-AR-4-DOCS-REVIEW | Documentation Review | docs/architecture.md, docs/testing/* (manual check) | Pass | 2025-12-04 | Evidence captured in Week14_Assessment and AR-4: Documentation issue closure notes.
AR-5 | Architectural | Track risks such as large-file performance, model drift, and forecast false positives with mitigation plans. | TC-AR-5-RISK-LOG | Process / Tracking | docs/risks-and-mitigations.md (AR-5) | Pass (initial baseline) | 2025-12-04 | Documented risks and mitigations; some are marked as “Evidence: to be addressed in future work” for transparency.